## Slide 1: Detection of QPOs in Neutron Star Light Curves Using Neural Networks
Project and Data Management Plan
Name: Sravanth Baratam
Student ID: 23001152
Supervisor: Dr. William Alston
Institution: University of Hertfordshire

## Slide 2: Background & Motivation
QPOs (Quasi-Periodic Oscillations) – Variations in the X-ray brightness of compact objects like black holes and neutron stars, often used in astrophysics and signal processing.
Why QPOs?
- Probe accretion physics near neutron stars.
- Challenges: Non-stationary noise, low signal-to-noise ratio.
- Why Neural Networks?
  Neutron star light curves exhibit stochastic noise (e.g., red noise from accretion flows) and non-stationary QPOs (drifting frequencies, variable amplitudes).
  NNs automatically learn temporal/spatial patterns without assuming stationarity, unlike Fourier methods that require fixed-frequency signals.

## Slide 3: Research Question & Objectives
Research Question:
Can neural networks and GANs improve QPO detection in neutron star light curves?
Objectives:
1. Develop GAN for synthetic light curves.
2. Train hybrid CNN-LSTM model for QPO analysis.
3. Validate against traditional methods.
4. Ensure ethical data practices.

## Slide 4: Develop GAN for synthetic light curves.
Develop a GAN for Synthetic Light Curves Build a Generative Adversarial Network (GAN) to simulate time series data resembling those observed from accreting black holes.
Train the GAN on properties derived from real X-ray data provided by the XMM-Newton telescope.
Validate the GAN's output by comparing its statistical properties (e.g., power spectrum, log-normal distribution) with those of real observational data.

## Slide 5: Project Plan & Timeline
Tasks:
- Literature review (Weeks 1–4).
- GAN development (Weeks 4–8).
- Model training (Weeks 6–10).
- Validation (Weeks 9–12).
Milestones:
- Interim presentation(PDM)
- Final submission

## Slide 6
Chart: PDM Gantt Chart
| Literature Review | Data Collection | GAN Development | NN Model Training | Draft Methodology | Validation & Analysis | Draft FPR | FPR
Start Date | 45691 | 45691 | 45691 | 45702 | 45708 | 45698 | 45716 | 45754
Duration(days) | 21 | 28 | 11 | 14 | 18 | 56 | 38 | 35

## Slide 7: Data Management Plan
Dataset Overview:
Source: XMM-Newton X-ray telescope.
Format: FITS files (Flexible Image Transport System), time-series X-ray data.
Variables: Time stamps, flux values, measurement errors.
Data Collection:
Primary data: XMM-Newton observations (via [XSA](https://www.cosmos.esa.int/web/xmm-newton/xsa)).
Synthetic data: Generated using GANs (simulated QPOs + red noise).
Metadata:
File types: `. fits` (observations)
Size: _GB (real), _GB (synthetic).
Structure: Organized directories with clear subfolder separation for real vs. synthetic datasets.

## Slide 8
Document Control:
GitHub: ` https://github.com/sravanth-space/ds_project`
Versioning: Semantic
Commits: Weekly commits with detailed log messages.
ReadMe File Contents:
Installation Guide: Dependencies (Python, TensorFlow, Keras, Astropy).
Data Handling: How to preprocess real and synthetic light curves.
Usage: Example scripts validation metrics.
Security & Storage:
Backups: GitHub + OneDrive (nightly syncs).
Access: Public repo on Github
Ethical Compliance:
GDPR: Not applicable (XMM-Newton data is publicly available.).
UH Ethics: Compliant (non-sensitive data).
Permissions: Granted via European Space Agency's (ESA) Open Access policy.
Ethical Collection: XMM-Newton data adheres to ESA ethical guidelines.

## Slide 9: Expected Results & Validation
GAN Validation:
Power spectrum match (synthetic vs. real).
Log-normal flux distribution.
NN Performance:
Accuracy >90% (QPO detection).
MAE <0.1 Hz (frequency estimation).

## Slide 10: Conclusion
In summary, this project leverages neural networks to overcome limitations of traditional QPO detection methods.

## Slide 11: Thank You